## Overview
OVERVIEW
Cost-Benefit Item: | Costs | Benefits | Description
PLAN A: In-house Development
Consultant time to develop system | 14440 |  | Developmental
Purchase necessary software platform | 2500 |  | Developmental
Plan B: Purchase Vertical Software Package
Purchase price for vendor package | 9000 |  | Developmental ($3000 x 3)
Tech support contract | 500 |  | Operational after 1st year (annual)
Consultant time to install, configure, and test | 4800 |  | Developmental
Costs and Benefits Common to Both Plans
Hardware | 5000 |  | Developmental
Consultant training time | 3900 |  | Developmental
Office staff maintenance, backup, and updating | 1768 |  | Operational (prorate for 1st year)
Eliminate overtime |  | 1989 | Operational (prorate for 1st year)
Eliminate additional position |  | 17680 | Operational (prorate for 1st year)
Eliminate daily errors |  | 2210 | Operational (prorate for 1st year)
The prorated operational expenses are for 40 of 52 weeks for Plan A, and 48 of 52 weeks for Plan B. The additional position is eliminated in both plans and is prorated for 6 of 12 months in both cases.
CIS251
S4 Written Assignment
Economic Feasibility Analysis

## Cost Benefit Summary
COST BENEFIT SUMMARY
DATA FOR PLAN A: In-House Development
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Costs:
Consultant time to develop system | Year 0: 14440
Purchase necessary software platform | Year 0: 2500
Hardware | Year 0: 5000
Consultant training time | Year 0: 3900
Office staff maintenance, backup, and update | Year 0: 1768
Total Costs: | 27608 | 0 | 0 | 0 | 0 | 0 | 27608
Benefits:
Eliminate overtime | 1989 | 1989 | 1989 | 1989 | 1989 | 1989
Eliminate additional position | 8840 | 17680 | 17680 | 17680 | 17680 | 17680
Eliminate daily errors | 2210 | 2210 | 2210 | 2210 | 2210 | 2210
Total Benefits: | 13039 | 21879 | 21879 | 21879 | 21879 | 21879 | 122434
DATA FOR PLAN B: Purchase Vertical Software Package
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Costs:
Purchase price for vendor package | Year 0: 3000; Year 1: 3000; Year 2: 3000
Tech support contract |  | 500 | 500 | 500 | 500 | 500
Consultant time to install, configure, and test | Year 0: 4800
Hardware | Year 0: 5000
Consultant training time | Year 0: 3900
Office staff maintenance, backup, and update | Year 0: 1768
Total Costs: | 18468 | 3500 | 3500 | 500 | 500 | 500 | 26968
Benefits:
Eliminate overtime | 1989 | 1989 | 1989 | 1989 | 1989 | 1989
Eliminate additional position | 8840 | 17680 | 17680 | 17680 | 17680 | 17680
Eliminate daily errors | 2210 | 2210 | 2210 | 2210 | 2210 | 2210
Total Benefits: | 13039 | 21879 | 21879 | 21879 | 21879 | 21879 | 122434

## Payback Analysis
PAYBACK ANALYSIS
PLAN A: In-House Development
|  | Cumulative |  | Cumulative
| Costs | Costs | Benefits | Benefits
Year 0 | 27608 | 27608 | 13039 | 13039
Year 1 | 0 | 27608 | 21879 | 34918
Year 2 | 0 | 27608 | 21879 | 56797
Year 3 | 0 | 27608 | 21879 | 78676
Year 4 | 0 | 27608 | 21879 | 100555
Year 5 | 0 | 27608 | 21879 | 122434
PLAN B: Purchase Vertical Software Package
|  | Cumulative |  | Cumulative
| Costs | Costs | Benefits | Benefits
Year 0 | 18468 | 18468 | 13039 | 13039
Year 1 | 3500 | 21968 | 21879 | 34918
Year 2 | 3500 | 25468 | 21879 | 56797
Year 3 | 500 | 25968 | 21879 | 78676
Year 4 | 500 | 26468 | 21879 | 100555
Year 5 | 500 | 26968 | 21879 | 122434
Payback: about 3 months into year 1

## ROI
RETURN ON INVESTMENT (ROI)
PLAN A: In-House Development
|  | Cumulative |  | Cumulative
| Costs | Costs | Benefits | Benefits
Year 0 | 27608 | 27608 | 13039 | 13039
Year 1 | 0 | 27608 | 21879 | 34918
Year 2 | 0 | 27608 | 21879 | 56797
Year 3 | 0 | 27608 | 21879 | 78676
Year 4 | 0 | 27608 | 21879 | 100555
Year 5 | 0 | 27608 | 21879 | 122434
ROI = (Total Benefits - Total Costs) / Total Costs |  |  | Total Benefits: | 122434
|  |  | Total Costs: | 27608
|  |  | Net | 94826
|  |  | ROI: | 343.5%
PLAN B: Purchase Vertical Software Package
|  | Cumulative |  | Cumulative
| Costs | Costs | Benefits | Benefits
Year 0 | 18468 | 18468 | 13039 | 13039
Year 1 | 3500 | 21968 | 21879 | 34918
Year 2 | 3500 | 25468 | 21879 | 56797
Year 3 | 500 | 25968 | 21879 | 78676
Year 4 | 500 | 26468 | 21879 | 100555
Year 5 | 500 | 26968 | 21879 | 122434
ROI = (Total Benefits - Total Costs) / Total Costs |  |  | Total Benefits: | 122434
|  |  | Total Costs: | 26968
|  |  | Net | 95466
|  |  | ROI: | 354%

## Present Value
NET PRESENT VALUE ANALYSIS (Using 10 % discount factor) | [5 empty] | 10%
PLAN A: In-House Development
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Costs | 27608 | 0 | 0 | 0 | 0 | 0
Factor (10%) | 1 | 0.90909 | 0.82645 | 0.75131 | 0.68301 | 0.62092
PV of Costs | 27608 | 0 | 0 | 0 | 0 | 0 | 27608
Benefits | 13039 | 21879 | 21879 | 21879 | 21879 | 21879
Factor (10%) | 1 | 0.90909 | 0.82645 | 0.75131 | 0.68301 | 0.62092
PV of Benefits | 13039 | 19890 | 18081.8182 | 16438.0165 | 14943.6514 | 13585.1376 | 95977.6237
| Year 4: Net Present Value: | 68369.6237
PLAN B: Purchase Vertical Software Package
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Costs | 18468 | 3500 | 3500 | 500 | 500 | 500
Factor (10%) | 1 | 0.90909 | 0.82645 | 0.75131 | 0.68301 | 0.62092
PV of Costs | 18468 | 3181.8182 | 2892.562 | 375.6574 | 341.5067 | 310.4607 | 25570.005
Benefits | 13039 | 21879 | 21879 | 21879 | 21879 | 21879
Factor (10%) | 1 | 0.90909 | 0.82645 | 0.75131 | 0.68301 | 0.62092
PV of Benefits | 13039 | 19890 | 18081.8182 | 16438.0165 | 14943.6514 | 13585.1376 | 95977.6237
| Year 4: Net Present Value: | 70407.6188